CS-134

PROFESSIONAL ISSUES AND SOFTWARE ENGINEERING

Attempt 2 questions out of 3

Question 1

(a)	Describe three alternative approaches to the software development process.

[12 marks]

(b)	What are the main strengths and weaknesses of each of the approaches described in part (a)?

[6 marks]

(c)	An insurance company that specialises in health insurance wishes to implement an electronic document management system. The basic idea is that all documents that are received by the company are scanned in and linked to the relevant record, together with any electronic documents which have been produced, so that all documentation held on a particular customer/policy/claim are available, linked together in electronic format. What development approach would you recommend for this software project? Give reasons for your answer.

[7 marks]

Question 2

(a)	Briefly describe the protection provided to intellectual property via copyright, patents and trademarks.

[9 marks]

(b)	Explain the term "Copyleft" and discuss what is meant by "Free Software" (as used by Richard Stallman and the Free Software Foundation).

[5 marks]

(c)	Recently there have been moves to introduce changes to the legislation in Europe to allow patent protection for computer programs. What are the main arguments for and against such a change?

[4 marks]

(d)	Consider the following two requests from a lecturer in the Computer Science department of a university to the university library:

(i) Can I have a report of the number and length of borrowings of each of the recommended texts for the module I teach?

(ii) Can I have a report detailing for each student taking the module that I teach, a list of the books borrowed by them and dates of each borrowing?

Discuss the legal and ethical issues that arise from these requests.

[7 marks]

Question 3

(a)	(i)	In the context of project management, explain the following terms: task, milestone,

critical path, and slack.

[6 marks]

(ii)	For each of the tasks listed below, determine the earliest and latest event time, the

slack, and whether or not the task is on the critical path. Draw a network chart and

highlight the critical path.

Task	Predecessor	Duration

A	None	90

B	A	30

C	A	40

D	B, C	20

E	C	90

F	C	30

G	D	30

H	G	30

I	D	40

J	F	40

K	E, H, I, J	60

L	K	10

[8 marks]

(b)	(i)	Explain and contrast white box testing and black box testing.

[4 marks]

(ii)	What type of program errors can be detected using static analysis?

[2 marks]

(c)	What is the Capability Maturity Model and what purpose does it serve?

[5 marks]